## Sheet1
[5 empty] | Fall Term | [9 empty] | Spring Term
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Planning
Client Conference Calls | bar: 2; 4; Fall Term 6; Fall Term 8; Fall Term 10
Project Planning | bar: 1 to 3
Install Software | bar: 3 to 4
Order Parts | bar: 4
Receive Parts | bar: Fall Term 8
Final Documentation
Modeling
Mechanical Modeling | bar: Fall Term 5 to Fall Term 8
Model Interaction with Sensors (software) | bar: Fall Term 6 to Fall Term 9
Computer Programming & Simulation | bar: Fall Term 9 to Fall Term 10
Assemble Mechanics | bar: Fall Term 10
Assemble Electrical Hardware
Combine Components
Testing
Software Unit Testing | bar: Fall Term 6 to Fall Term 10
Integration Testing
Final Testing
Winter Term
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Planning
Client Conference Calls | bar: 2; 4; Winter Term 6; Winter Term 8; Winter Term 10
Project Planning
Install Software
Order Parts
Receive Parts
Final Documentation
Modeling
Mechanical Modeling
Model Interaction with Sensors (software)
Computer Programming & Simulation | bar: 1 to Winter Term 5
Assemble Mechanics | bar: 1 to Winter Term 6
Assemble Electrical Hardware | bar: 1 to Winter Term 7
Combine Components | bar: Winter Term 6 to Winter Term 8
Testing
Software Unit Testing | bar: 1 to 3
Integration Testing | bar: Winter Term 8 to Winter Term 10
Final Testing
Spring Term
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Planning
Client Conference Calls | bar: 2; 4; Spring Term 6; Spring Term 8; Spring Term 10
Project Planning
Install Software
Order Parts
Receive Parts
Final Documentation | bar: Spring Term 9 to Spring Term 10
Modeling
Mechanical Modeling
Model Interaction with Sensors (software)
Computer Programming & Simulation
Assemble Mechanics
Assemble Electrical Hardware
Combine Components
Testing
Software Unit Testing
Integration Testing | bar: 1 to Spring Term 8
Final Testing | bar: Spring Term 9 to Spring Term 10